## Bug Reports
Bug ID | Summary | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Environment | Browser | OS | Screen Resolution | Reporter | Assignee | Date Reported | Date Fixed | Screenshot/Attachment | Notes
BUG-001 | Contact form submits with invalid email format | The contact form allows submission even when an invalid email address is entered (e.g., 'test@'), bypassing client-side validation. | 1. Navigate to contact.html 2. Enter 'John Doe' in Name field 3. Enter 'invalid@' in Email field 4. Enter 'Test message' in Message field 5. Click Submit button | Form should display error message 'Please enter a valid email address' and prevent submission | Form submits successfully without validation error. Invalid email is processed. | High | P2 | Open | Production | Chrome 125.0.6422 | Windows 11 | 1920x1080 | Computer |  | 2026-02-15 |  | screenshots/bug-001.png | Email validation regex needs to be updated
BUG-002 | Navigation menu overlaps content on mobile (320px) | On mobile viewport (320px width), the navigation menu overlaps the main content area, making text unreadable. | 1. Open application in Chrome DevTools 2. Set viewport to 320px × 568px 3. Navigate to Services page 4. Observe header and content positioning | Navigation menu should collapse into hamburger menu or adjust to mobile viewport without overlapping content | Full navigation menu displays and overlaps first 2 paragraphs of content. Text is not readable. | Medium | P2 | In Progress | Production | Chrome 125.0.6422 | Windows 11 | 320x568 (mobile) | Computer | Dev Team | 2026-02-14 |  | screenshots/bug-002-mobile.png | CSS media query breakpoint issue
BUG-003 | Image broken on Culture page in Firefox | The hero image on culture.html does not load in Firefox browser, showing broken image icon instead. | 1. Open Firefox browser (latest version) 2. Navigate to culture.html 3. Observe hero image section | Hero image should load and display correctly as it does in Chrome | Broken image icon appears. Console shows 404 error for image path | Low | P3 | Open | Production | Firefox 126.0 | Windows 11 | 1920x1080 | Computer |  | 2026-02-15 |  | screenshots/bug-003-firefox.png | Possible file path case sensitivity issue
BUG-004 | [7 empty] | Open |  |  |  |  | Angelica Soete
BUG-005 | [7 empty] | Open |  |  |  |  | Angelica Soete
BUG-006 | [7 empty] | Open |  |  |  |  | Angelica Soete
BUG-007 | [7 empty] | Open |  |  |  |  | Angelica Soete
BUG-008 | [7 empty] | Open |  |  |  |  | Angelica Soete
BUG-009 | [7 empty] | Open |  |  |  |  | Angelica Soete
BUG-010 | [7 empty] | Open |  |  |  |  | Angelica Soete
BUG-011 | [7 empty] | Open |  |  |  |  | Angelica Soete
BUG-012 | [7 empty] | Open |  |  |  |  | Angelica Soete
BUG-013 | [7 empty] | Open |  |  |  |  | Angelica Soete

## Bug Legend
BUG REPORT LEGEND
SEVERITY LEVELS:
Critical | System crash, data loss, security vulnerability
High | Major feature broken, blocks testing
Medium | Feature partially works, workaround available
Low | Minor issue, cosmetic, nice-to-have
PRIORITY LEVELS:
P1 | Must fix immediately (blocker)
P2 | Fix before release
P3 | Fix if time permits
P4 | Future enhancement
STATUS OPTIONS:
Open | Bug reported, not yet assigned
In Progress | Developer working on fix
Resolved | Fix completed, awaiting verification
Closed | Fix verified and deployed
Reopened | Issue persists after fix attempt
ENVIRONMENT:
Production | Live website
Staging | Pre-production testing environment
Development | Local development environment